## Cover Page
E-Learning Management
Product Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | Academy Project Solutions
Role
Signature
Date
Release ID: QTAD-PBL / 2.0.0 / 30-Mar-2015 |  |  |  | C3: Protected
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Product Backlog Instructions C3: Protected Controlled Copy
Backlog Worksheet
This sheet has to be filled while doing "Create Product Backlog" task in the Initial Envisioning Phase.
The Product backlog worksheet contains a list of features/requirements that the business would want to implement in an application. This worksheet would continue to exist from the beginning to the end of the project. The Product Owner maintains it by adding, modifying, removing any of the items listed there. They can also change the priority of the items so long as they are not being worked by the team in the ongoing Sprint. Most of the re-ordering would happen just before the Sprint Planning meeting. To ensure this kind of continuous update, this worksheet could be re-visited during periodic intervals once during the release elaboration Phase and thereafter during the project execution. The changes to the Product backlog could be triggered from several sources in terms of inclusion of new features / bugs/ known issues based on the stakeholder requests and the effort, schedule for the same would also be re-visited in the product backlog worksheet. Fill the following fields in the product backlog worksheet for each feature.
| User Story ID | <Provide unique ID for each User story>
| User Story Name | <Provide the theme/name of the User story or a high level requirement> Eg: User login Registration Mail notification
| User Story Role | < Provide who would be end User of the User story>. Details of who would use that functionality Eg:End User Admin Teacher Conference attendee
| User Story Details | <Provide description of what the User want> Provide details on "As a/an" particular user what the user wants. Eg: As a conference attendee, I want to be able to register online
| Acceptance criteria | <Specify the Acceptance criteria> Acceptance criteria define the boundaries of a user story, and are used to confirm when a story is completed and working as intended. So for the above example, the acceptance criteria could include: A user cannot submit a form without completing all the mandatory fields Information from the form is stored in the registrations database.
| Sprint | Sprint in which the user story is planned to completed. Select it from the drop down. Story Point is given in Fibonacci series of upto 21. For any User story if the estimation goes beyond 21, then the user story has to be broken down.
| Story point | A story point is a metric used in agile project management and development to determine (or estimate) the difficulty of implementing a given story. Select the story point that will be assigned to the user story from the drop down (in Fibonacci series) during the sprint planning meeting while estimating an user story.
| Done | Yes/No field, that can be selected from drop down based on an user is completed or not
| Added in Sprint | Provide sprint number when the particular User Story was handled
| Closed in sprint | Provide sprint number when the particular User Story was completed
| Actual Story Points | Actual story point burned for an user story while developing. Select from the drop down (in Fibonacci series)
Charts
| Sprint | This value is non-editable. Represents the Sprint numbers
| Story Points remaining | Enter the total story points calculated for the Sprint.
| Done | Enter the total story points that was "Done" in the sprint
| Variation | This value is non-editable. Variation is calculated as [(Current sprint's story point remaining + done) - (Previous sprint's story point remaining + done) + Previous sprint's variation]
| Percent Complete | Percentage completed is calculated as [(Done story point of the sprint/(Done story point + story point remaining)) *100]
| Release Burn Down Chart | 1. A typical release Burn Down chart would enable the Product Owner to assess as to how each iteration is progressing towards realizing the release goal. They would be able to assess the number of features that are going to make it (or) not make it to the release based on the number of features delivered by the team in each iteration. 2. Based on the progress being made by the team, the Product Owner may decide to add more Sprints within a release (if it is a feature driven release) or cut down some of the features from the Release backlog (if it is a Date driven release). The release burn down chart would be automatically plotted based on the data given on the Release burn down table with story points remaining and the done.

## Backlog
Product Backlog E-Learning Management Project ID: A002 C3: Protected Controlled Copy
Done
User Story Id | User Story Name | User Story Role | User Story Details | Acceptance criteria | Priority | Sprint | Story Point | Done | Added in Sprint | Closed in sprint | Actual Story Points
US_1 | Admin Login | Admin | As an Admin I want the system to make first user as admin who can initiate functionality of system | 1-Users should have option to select their role option - user/Admin 2-Admin should select the Admin option. 2-Admin's User id and password should be pre-loaded in the database, which can be used to log in. | Critical | 1 | 1
US_2 | User Registration | User | As an User I want the system to procure the fundamental details of the user | 1-When the user clicks on the signup, it should re-direct to signup form. 2-Although all fields in the user table are required, a check needs to be done Field of User: Name should be in range 4-50 DOB should be entered and the age should not be less than 18. Contact number should be of 10 digits Password should be of minimum 6 letters with special characters included. Note - Trainees can add/neglect fields that will be appropriate and validations should be handled for all fields | Critical | 1 | 2
US_3 | User Data | User | As an User I want the system to procure the fundamental details of the user | 4-If user failed to provide Name an error in red should be shown as “Name should be of minimum 4 letters” 5-If user failed to provide DOB or age <18, an error in red should be shown as “age should be of minimum 18” 6-If user failed to provide Contact, an error in red should be shown as “Contact should be of Integer and minimum of 10 digits” 7-If user failed to provide valid password, an error in red should be shown as “Invalid password”, and valid password structure 8-If user failed to provide every mandatory fields, an error in red should be shown as “Address is Mandatory” 9-Clicking on signup button with valid values, the customer will be redirected to login page 10- Role shouldalso be selected during Registration as Learner/Vendor - radio button can be used here to select the role Note - Use Radio buttons, Drop downs, check boxes, autogenerated Ids etc wherever possible. | Critical | 1 | 3
US_4 | User Authentication | User | As an User I want the system to authenticate the user credentials of the registered user and proceed with user role. | A registered Employee – is able click ‘Login’ link, after keying in ‘Employee ID’ & ‘Password’ field and get his credentials authenticated with the existing database entry. | Critical | 1 | 1
US_5 | Admin Home | Admin | As an Admin I want the system to raise admin ui when Admin is logged in | 1-If the Role is received as Admin, Admin ui should pop up 2-Admin can see the user list 3-Admin can add a filter user list based on the role 4-Admin can add/update a user/vendor on clicking “add user” link 5-Admin can modify the role of user 6-Admin can block the user/vendor 7-Admin can act like a vendor (should have all write to access data) | Critical | 1 | 5
US_6 | Learner Home | Learner | As an Learner I want the system to raise Learner ui when Learner is logged in | 1-If the Role is received as Learner, Learner ui should pop up which have 3 links profile, Purchase history, Online Services 2-If Learner click on profile, a form should pop up and he can edit his information. Field: Name and id will be locked on edit, other fields can be edited 3-In profile form, Learner can also deactivate his account by clicking on “deactivate” 4-Deactivate account should be confirmed using confirm box 5-Clicking on Purchase History, Learner should be redireacted to his Purchase History. | Critical | 1 | 3
US_7 | Learner Details | Learner | As an Learner I want the system to raise Learner ui when Learner is logged in | 6-Clicking on Purchase History link, Learner should list the E learnings Purchased by him. 7-3rd link, which will be the landing page of Learner home, should contain all the available services from different vendor, though he can Make Payment for any service. 8-On clicking Maye Payment, Learner should be redirected to payment receipt link, which should be confirmed by Learner whether he is sure to purchase that service. Service should contain all the ids of courses that should be accessed after purchase. 9-On confirming the Learner should be redirected to availed services in profile which contain all the available purchased services in database. 10-If Learner failed to confirm he should be redirected to available service page 11-On clicking on logout Learner should be logout of the system. | Critical | 1 | 3
US_8 | Vendor Home | Vendor |  | 1-If the Role is received as Vendor, vendor ui should pop up which should have 3 links- profile, history, Online Services 2-If user click on profile, a form should pop up and he can edit his information. Field: Name and id will be locked on edit, other fields can be edited. 3 In profile form, user can also deactivate his account by clicking on “deactivate” 4-Deactivate account should be confirmed using confirm box | Critical | 1 | 2
US_9 | Vendor Details | Vendor | As a Vendor I want the system to raise vender ui when a vendor is logged in. | 5-Clicking on Orders, user should be redirected to the Prchased done for his services. 6-Clicking on Orders link, user should list all the orders / purchased made in favor of his service 7 Clicking Services / Products should list all his services / Products. 8 Vendor should have the option to activate / deactivate them 9 Deactivated services will not be viewable to Learner | Critical | 2 | 5
US_10 | Listing Service | Vendor | As a vendor I want to add services in the system which can be availed by subscriber | 1-Service can be list by Admin or vendor. Service listing such as Online Training (Synchronous eLearning / Real Time) Downloadable Materials Online Test / Certification Webinar Help Desk etc 2-If Admin is adding service, he has to provide the service with vendor object 3-If vendor is adding service, he only has to fill the add service 4-Admin or vendor can activate or deactivate a service Deactivated services will not be viewable to Learner | Medium | 2 | 5
US_11 | Listing Courses | Admin & Vendor | As Admin & Vendor I want to add courses to the system and link it with service | 1-Admin or vendor can add a course 2-Admin or vendor can edit a course 3-On clicking on edit a form should be pop up With valid input clicking on Add/update will update the database 4-Admin or vendor can activate or deactivate a course Note: This refers to the Asynchronous eLearning - where learners complete self-paced online training | Medium | 2 | 5
US_12 | Search Option | Admin/Vendor/User | As Admin/Vendor/User I want the system to allow to search | 1-Search option should be available for all user types to search for the course 2-Search should be based on the category – vendor/course/course category (instructor led/self learning/assessment) 3-On selecting the vendor/course category it should list all the course with minimum details like vendor/duration of the course etc Use pagenation to display the search list. 4-User should be able to select the course from the list which would open the course details page 5-From where, the user should be able to register for the course and proceed to payment 6-From where, if Vendor/Admin should be able to edit/delete course Note - payment has to be mocked. | Critical | 2 | 5
US_13 | Write review | Learner | As Learner I want the system to write/view review for a course | 1-Learner should be able to write review on completing the course 2-Learner should be able to view reviews while seeing the course details. | Low | 2 | 2
US_14 | Send Notification | Learner | As Learner I want the system to send notification | 1-System should have option to subscribe themselves for getting notifications for new courses 2-System should have option to send notification to subscribed Learners when new courses are added to the system | Low | 2 | 3
US_15 | Show new courses | Learner | As Learner I want the system to Show new courses on home page | 1-Show updates of new courses on the Learners home page (courses added in last 30 days) | Low | 2 | 1
US_16 | Log out | Users | As Users we want to log out of the system | 1-All Users should be able to log out of the system | Critical | 1 | 1

## Charts
Release Burndown
Only edit shaded columns, others are calculated
Sprint | Story points |  |  | Percent Complete | Min | Max
| Remaining | Done | Variation
1 | 100 | 75 | 0 | 43% | 0 | 100
2 | 170 | 150 | 145 | 47% | -145 | 25
3 | 190 | 120 | 135 | 39% | -135 | 55
Yes
No

## Sheet1 (hidden)
0
5
10
20
30
50
80
130
200
400
1000